## Sheet1
Related User Story | Assigned To | Initial Estimate | Amount Remaining After…
|  |  | Week 1 | Week 2
Create Employee | Daniel | 3 | 3 | 0
Delete Employee | Daniel | 3 | 3 | 0
View Employee | Daniel | 1 | 1 | 0
Demote Employee from manager for a group | Daniel | 2 | 2 | 0
Promote Employee to Manager for a Group | Daniel | 2 | 2 | 0
View Projects | Daniel | 1 | 1 | 0
View Employee in groups | Daniel | 1 | 1 | 0
View Groups | Daniel | 1 | 1 | 0
Create Groups | Daniel | 3 | 3 | 0
Remove Group from Project | Daniel | 2 | 2 | 0
Assign Group to Project | Daniel | 2 | 2 | 0
Edit Title of Project | Daniel | 1 | 1 | 0
View Groups | Daniel | 2 | 2 | 0
Delete Groups | Daniel | 2 | 2 | 0
Edit Description of Project | Daniel | 1 | 1 | 0
Test Model Classes | Jacob | 6 | 4 | 0
Test ViewModel Classes | Jacob | 8 | 6 | 0
Test Controller Classes | Jacob | 10 | 7 | 4
UML Class Diagram | Jacob | 4 | 2 | 0
Use Case Scenarios | Jacob | 2 | 0 | 0
Estimate Totals |  | 57 | 46 | 4