## Sheet1
Related User Story |  | Initial Estimate | Amount Remaining After…
| Assigned To |  | Week 1 | Week 2
View Task | Jacob | 1 | 0 | 0
Create Task | Jacob | 1 | 1 | 0
Update Stage for Task | Daniel | 1 | 1 | 0
Restrict Column to group | Daniel | 2 | 2 | 0
edit group/ project should assign member/group using separate box for list of options and list of currently selected items | Daniel | 4 | 0 | 0
Assign Task | Jacob | 2 | 2 | 0
<OPTIONAL> display history for task on view (aka log) |  | 2 | 2 | 2
<OPTIONAL> post comment for task |  | 2 | 2 | 2
|  | 15 | 10 | 4