## Sheet1
Related User Story |  | Initial Estimate | Amount Remaining After…
| Assigned To |  | Week 1 | Week 2
Editing groups/projects when adding a member and saving, save only persists the selected members. |  | 3 | 0 | 0
Assigning tasks is not consistently displaying the correct set of users available. |  | 3 | 0 | 0
Add datetime to comments. |  | 1 | 0 | 0
Update permissions to allow users on a project to freely create/edit/delete task; should only restrict who can be assigned to a task. |  | 2 | 0 | 0
View my assigned tasks. (Desktop) | Jacob | 2 | 0 | 0
View my available tasks. (Desktop) | Jacob | 2 | 0 | 0
View task details. (Desktop) |  | 2 | 0 | 0
Update stage for a task. (Desktop) |  | 2 | 0 | 0
Create a task. (Desktop) |  | 2 | 0 | 0
<optional> Implement post comments (Desktop) |  | 3 | 0 | 0
|  | 22 | 0 | 0