## Sheet1
Related User Story |  | Initial Estimate | Amount Remaining After…
| Assigned To |  | Week 1 | Week 2
That User Story
View Projects | Daniel | 1 | 0 | 0
View Board for my Project | Daniel | 1 | 1 | 0
failed login (bad credentials) does not generate any feedback | Jacob | 1 | 1 | 0
edit group/ project should assign member/group using separate box for list of options and list of currently selected items | Jacob | 4 | 4 | 4
show error when adding group/project on the modal instead of the page behind the modal | Daniel | 2 | 2 | 0
add support for search/filtering large lists | Jacob | 2 | 1 | 0
user should be able to view (but not edit) users, groups, and projects; | Daniel | 1 | 0 | 0
when adding group to project that has a different manager, should require other manager to access project and approve add before fully adding to project | Jacob | 3 | 0 | 0
delete project is failing | Daniel | 1 | 0 | 0
forms should clearly indicate required fields | Daniel | 1 | 0 | 0
should not be able to remove user that is manager for a group or project lead | Daniel | 2 | 1 | 0
Edit Board for Project I manage | Daniel | 3 | 2 | 0
View Board for my Project I am apart of | Daniel | 1 | 0 | 0
|  | 23 | 12 | 4