## Sheet1
Related User Story |  | Initial Estimate | Amount Remaining After…
| Assigned To |  | Week 1 | Week 2
Edit Group | Daniel | 2 | 0 | 0
Edit Project | Daniel | 2 | 0 | 0
Assign/Remove Group to/from Project | Daniel | 2 | 0 | 0
Assign a task to myself | Jacob | 1 | 1 | 0
View Task | Jacob | 1 | 0 | 0
Create a Task on the Board of a Project for my Group | Jacob | 2 | 1 | 0
Update Stage of my assigned Task | Jacob | 1 | 0 | 0
Assign a Task on a Board from a Project for my Group to an Employee in my Group | Jacob | 2 | 2 | 2
Assign/Remove Group(s) to/from Stage of Project | Jacob | 2 | 2 | 2
View a history of events for a Task (Optional) |  | 2 | 2 | 2
Post a comment to a Task on the Board of a Project for my Group (Optional) |  | 3 | 3 | 3
|  | 20 | 11 | 9