## Sheet1
Related User Story | Initial Estimate | Amount Remaining After…
|  | Week 1 | Week 2
That User Story
Create Employee | 3 | 3 | 0
Delete Employee | 3 | 3 | 0
View Employee | 1 | 1 | 0
Demote Employee from manager for a group | 2 | 2 | 0
Promote Employee to Manager for a Group | 2 | 2 | 0
View Projects | 1 | 1 | 0
View Employee in groups | 1 | 1 | 0
View Groups | 1 | 1 | 0
Create Groups | 3 | 3 | 0
Remove Group from Project | 2 | 2 | 0
Assign Group to Project | 2 | 2 | 0
Edit Title of Project | 1 | 1 | 0
View Groups | 2 | 2 | 0
Delete Groups | 2 | 2 | 0
Edit Description of Project | 1 | 1 | 0
Estimate Totals | 27 | 27 | 0