## Sheet1
Related User Story |  | Initial Estimate | Amount Remaining After…
| Assigned To |  | Week 1 | Week 2
View Task | Daniel | 1 | 0 | 0
Create Task | Daniel | 1 | 1 | 0
Update Stage for Task | Jacob | 1 | 1 | 0
edit group/ project should assign member/group using separate box for list of options and list of currently selected items | Jacob | 4 | 4 | 4
Assign Task | Daniel | 2 | 2 | 0
<OPTIONAL> display history for task on view (aka log) |  | 2 | 2 | 2
<OPTIONAL> post comment for task |  | 2 | 2 | 2
|  | 13 | 12 | 8