## Sheet1
Related User Story | Initial Estimate | Amount Remaining After…
|  | Week 1 | Week 2
That User Story
View, Create, and Delete Employee | 0.5 | 0 | 0
View Projects | 0.5 | 0 | 0
View Groups and employees in said group | 0.5 | 0 | 0
View, Create, and Delete Groups | 0.5 | 0 | 0
View, Create, and Delete Projects | 0.5 | 0 | 0
Assign/Remove Group to/from Project | 0.5 | 0 | 0
View Board for my Project | 1 | 1 | 0
View and Edit a Board for my Project | 1 | 1 | 0
| 5 | 2 | 0